## 14-Week Gantt Schedule
FindMate — 14-Week Project Work Breakdown Schedule and Milestone Gantt Chart
Course: CSE0613316 — Software Project Design & Development Lab ¦ Autumn 2026 ¦ UITS Dhaka ¦ Lead Dev: Abu Nasim (211014022) ¦ QA Lead: Rimon Chandra Bhowmik (211014035)
WBS | Work Breakdown Task Description | SDLC Phase | Primary Assignee | Deliverable Artifact | Start | End | Duration | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Milestone | Status
PHASE 1: INCEPTION & REQUIREMENTS ANALYSIS (Weeks 1 – 3)
1.1 | Problem Definition & Candidate Screening | Inception | Abu Nasim | Problem Statement & Persona Models | Week 1 | Week 1 | 1 wk | ■ | [13 empty] | — | Completed
1.2 | Stakeholder Identification & Persona Modeling | Inception | Rimon C. Bhowmik | Stakeholder & User Analysis Matrix | Week 1 | Week 2 | 2 wks | ■ | ■ | [12 empty] | — | Completed
1.3 | SRS Formulation & Feasibility Study | Inception | Abu Nasim & Rimon C. | Formal SRS Document & Feasibility Report | Week 2 | Week 2 | 1 wk |  | M1 | [12 empty] | ★ M1 | Completed
1.4 | High-Level Architecture & Use Case Specs | Inception | Abu Nasim | System Boundaries & 4 Use Case Models | Week 3 | Week 3 | 1 wk |  |  | ■ | [11 empty] | — | Completed
PHASE 2: ELABORATION & SYSTEM ARCHITECTURE (Weeks 4 – 6)
2.1 | Detailed UML Design (ERD, Sequence, DTO) | Elaboration | Abu Nasim & Rimon C. | Chen ERD, Crow Schema & 5 Sequence Models | Week 4 | Week 4 | 1 wk |  |  |  | M2 | [10 empty] | ★ M2 | Completed
2.2 | UI/UX Wireframing & Figma High-Fi Prototype | Elaboration | Abu Nasim | Figma Design System & 7 View Mockups | Week 4 | Week 5 | 2 wks |  |  |  | ■ | ■ | [9 empty] | — | Completed
2.3 | Stack Scaffolding (Go Gin + React + Tailwind) | Elaboration | Abu Nasim | Go Gin Router & React 19 Frontend Shell | Week 5 | Week 6 | 2 wks |  |  |  |  | ■ | ■ | [8 empty] | — | Completed
2.4 | Monorepo Setup & CI Environment Scaffolding | Elaboration | Rimon C. Bhowmik | GitHub Repo Scaffolding & Initial Workflows | Week 6 | Week 6 | 1 wk | [5 empty] | ■ | [8 empty] | — | Completed
PHASE 3: CONSTRUCTION & ITERATIVE IMPLEMENTATION (Weeks 7 – 10)
3.1 | Sprint 1: User Auth, OAuth & Profile Engine | Construction | Abu Nasim | JWT Auth, OAuth Providers & Profile API | Week 7 | Week 7 | 1 wk | [6 empty] | M3 | [7 empty] | ★ M3 | Completed
3.2 | Sprint 2: Micro-Lobbies & Tag Matching Engine | Construction | Abu Nasim | Discover Feed, Taxonomy Tags & Match Score | Week 7 | Week 8 | 2 wks | [6 empty] | ■ | ■ | [6 empty] | — | Completed
3.3 | Sprint 3: Pitch Vetting Queue & Squad Chat | Construction | Abu Nasim & Rimon C. | Application Pitch Engine & Squad Chat Rooms | Week 8 | Week 8 | 1 wk | [7 empty] | M4 | [6 empty] | ★ M4 | Completed
3.4 | Sprint 4: Peer Reputation & Admin RBAC Center | Construction | Abu Nasim | 5-Star Rating Algorithm & Moderation Hub | Week 9 | Week 9 | 1 wk | [8 empty] | ■ | [5 empty] | — | Completed
3.5 | Automated Test Suite (31 Tests, 99% Coverage) | Construction | Rimon C. Bhowmik | Node.js + Go Native Test Harness (31 TCs) | Week 9 | Week 10 | 2 wks | [8 empty] | ■ | M5 |  |  |  |  | ★ M5 | Completed
PHASE 4: TRANSITION, VERIFICATION & RELEASE (Weeks 11 – 14)
4.1 | End-to-End User Journeys & Security Hardening | Transition | Abu Nasim & Rimon C. | OWASP ASVS Verification & Boundary Audits | Week 11 | Week 11 | 1 wk | [10 empty] | ■ |  |  |  | — | Completed
4.2 | Automated Multi-Job CI/CD (GitHub Actions) | Transition | Abu Nasim | Parallel Multi-Job GitHub Actions Pipeline | Week 12 | Week 12 | 1 wk | [11 empty] | M6 |  |  | ★ M6 | Completed
4.3 | Staging Deployment & Live Viva Demonstration | Transition | Abu Nasim & Rimon C. | Staging Deployment & Viva Demo Presentation | Week 13 | Week 13 | 1 wk | [12 empty] | M7 |  | ★ M7 | Completed
4.4 | Final Capstone Report Polish & Release v1.0.0 | Transition | Abu Nasim & Rimon C. | Formal 13-Section Capstone Report & v1.0.0 | Week 14 | Week 14 | 1 wk | [13 empty] | M8 | ★ M8 | Completed
EXECUTIVE PROJECT METRICS & PERFORMANCE BENCHMARKS
Total Schedule Duration |  | 14 Weeks (On Schedule) |  |  |  |  | Planned Effort |  |  | 320 Person-Hours
Actual Logged Effort |  | 305 Person-Hours |  |  |  |  | Effort Variance |  |  | -15 Hours (-4.69% Favorable)
Milestone Gates Completed |  | 8 of 8 Milestones Passed (100%) |  |  |  |  | Total Verification Test Cases |  |  | 31 / 31 Passed (100% Pass Rate)
Backend & Business Logic Coverage |  | 99.00% Line Coverage (405 / 409 Stmts) |  |  |  |  | Direct Financial Expenditure |  |  | $0.00 (100% Open-Source & Free-Tier Cloud)
MILESTONE GATE DICTIONARY & VERIFICATION CRITERIA
Gate ID | Week | Gate Name & SDLC Scope | Verification Criteria & Produced Artifacts |  |  |  |  | Status & Attainment Record
M1 | Week 2 | SRS & Feasibility Baselined | Full functional (FR-1..FR-12) & non-functional requirements formalised; feasibility validated. |  |  |  |  | APPROVED (100% on-time, 0-day variance)
M2 | Week 4 | System Architecture & UML Baselined | Chen ERD, Crow's Foot schema, Class DTO, and 5 temporal Sequence diagrams completed. |  |  |  |  | APPROVED (Architectural integrity verified)
M3 | Week 7 | Core Engine MVP Operational | JWT authentication, OAuth identity provider linking, and micro-lobby creation live. |  |  |  |  | ACHIEVED (Scaffolding verified before mid-term)
M4 | Week 8 | Mid-Term Evaluation Defense | Instructor presentation of discovery feed, pitch application vetting, and squad group chat. |  |  |  |  | DEFENDED (Mid-term feedback integrated into sprint)
M5 | Week 10 | QA Test Verification Exit Gate | Automated execution of 31 test cases (27 native Node.js + 4 Go unit tests), 99.00% coverage. |  |  |  |  | PASSED (Quality exit criteria 100% satisfied)
M6 | Week 12 | Automated Multi-Job CI/CD Operational | GitHub Actions parallel runners configured for Node.js 20 and Go 1.22 with strict exit gates. |  |  |  |  | DEPLOYED (Automated build & test pass on every push)
M7 | Week 13 | Final Viva Voce & Demonstration Defense | Formal demonstration of seeker pitch vetting, squad messaging, and administrative RBAC hub. |  |  |  |  | CLEARED (Demonstration and oral viva approved)
M8 | Week 14 | Official Project Delivery v1.0.0 | Complete 13-section capstone report, release v1.0.0 tagged, GitHub documentation hub published. |  |  |  |  | DELIVERED (Final release signed off for submission)